## EX13.1 Answers
EX13.1
Given the diagram shown in figure EX 13.1, with activities A through G and duration times,
a. | Identify the paths and path duration times.
| Path | Duration Time
b. | Determine the critical path

## EX13.3 Answers
EX13.3
Calculate ES, LS, EF, LF and slack time for the activities in Exercise 13.1.
Activities | Duration Time | ES | LS | EF | LF | Slack Time
A
B
C
D
E
F
G
Path | Duration Time | ES | LS | EF | LF | Slack Time
AD
BE
CFG

## EX13.11 Answers
EX13.11
PERT - Probabilistic | [5 empty] | Length of Project = |  |  |  | Project Variance
Number of Critical Path(s) =
Activity Name | Description | Predecessor | Optimistic time (o) | Most likely time (m) | Pessimistic time (p) | Activity Name | On Critical Path | Average Time | Earliest Start | Latest Start | Earliest Finish | Latest Finish | Total Slack | Activity Variance
A | Design |  |  |  |  | A
B | Budget estimate |  |  |  |  | B
C | Permits |  |  |  |  | C
D | Bid process |  |  |  |  | D
E | Subcontractor buyout |  |  |  |  | E
F | Startup |  |  |  |  | F
G | New additional construction |  |  |  |  | G
H | Cooling tower procurement |  |  |  |  | H
I | Cooling tower installation |  |  |  |  | I
J | LOX/fuel tank |  |  |  |  | J
K | Boiler procurement |  |  |  |  | K
L | Boiler installation |  |  |  |  | L
M | Abate old boiler |  |  |  |  | M
N | Chiller procurement |  |  |  |  | N
O | Chiller installation |  |  |  |  | O
P | Generator procurement |  |  |  |  | P
Q | Generator installation |  |  |  |  | Q
R | Final inspection/testing |  |  |  |  | R
S | [5 empty] | S
T | [5 empty] | T
U | [5 empty] | U
V | [5 empty] | V
W | [5 empty] | W
X | [5 empty] | X
Y | [5 empty] | Y
Z | [5 empty] | Z
| Target Time | 147 |  | Target Probability
| Probability |  |  | Time
| Target Time | 150
Probability
| Target Time | 152
Probability
NOTE****** | PLEASE USE THE SCENARIO IN CHAPTER 13 ON PAGE 341 AND ADDRESS THE FOLLOWING:
Consider the challenges involved in project management of a construction project of this magnitude. What are some of the most significant challenges you would anticipate from managing this project?
Which management tools or methods described in Chapter 13 of Quantitative Methods and in other readings in the course might be useful in addressing these challenges, and why?
Identify 2–3 key challenges you would anticipate in managing this major construction project.
Which management tools and methods described in this and previous weeks' Learning Resources would be most appropriate to use in addressing these challenges? Provide a rationale for your assertions.