Laura Thompson needs to plan and manage a local construction project. The following table describes the relationships between the activities that need to be completed:

| ACTIVITY | Day A | Day M | Day B | Immediate Predecessors |
| --- | --- | --- | --- | --- |
| A | 4 | 8 | 13 |  |
| B | 4 | 10 | 15 | A |
| C | 7 | 14 | 20 | B |
| D | 9 | 16 | 19 | B |
| E | 6 | 9 | 11 | B |
| F | 2 | 4 | 5 | D,E |
| G | 4 | 7 | 11 | C,F |
| H | 3 | 5 | 9 | G |
| I | 2 | 3 | 4 | G,H |

- Determine the expected times and variances for each activity.

- Construct a project network for this problem

- Determine the EST,EFT,LST,LFT, and slack for each activity. Also determine the critical path and project completion time.

- What is the probability that the project will be finished in less than 57 days.

- What is the probability that the project will need at least 50 days?