You are the project manager for creating a new printer driver.  There are four modules in the driver.  Each module is to take one day and is budgeted for $1,000 per module.  The modules are scheduled to be completed sequentially.  Today is the end of day 3 and your senior management has asked for a progress report.

Using the project status chart below, calculate the values required and provide a verbal interpretation of what the answer means.

| TASK | DAY 1 | DAY 2 | DAY 3 | DAY 4 | STATUS AT END OF DAY 3 |
| --- | --- | --- | --- | --- | --- |
| Module 1 | S--F |  |  |  | Complete, spent $1,000 |
| Module 2 |  | S--PF | --F |  | Complete, spent $1,200 |
| Module 3 |  |  | PS—S—PF |  | Half done, spent $600 |
| Module 4 |  |  |  | PS—PF | Not yet started |
| S – Start |  |  |  |  |  |
| F – Finish |  |  |  |  |  |
| PS – Planned Start |  |  |  |  |  |
| PF – Planned Finish |  |  |  |  |  |

| WHAT IS: | CALCULATION | ANSWER | INTERPRETATION OF THE ANSWER |
| --- | --- | --- | --- |
| BCWS | 1,000 + 1,000 + 1,000 | 3,000 | We should have done $3000 worth of work. |
| BCWP | 2,800 / 3,000 | 93% | 93% of the work IS done on the current budgeted basis. |
| ACWP | 1,000 + 1,200 + 600 | 2,800 | We have done $2800 worth of work. |
| BAC | 1,000 + 1,000 + 1,000 + 1,000 | 4,000 | We budgeted $4,000 for the total job. |
| CV | BCWP - ACWP 93% - 2,800 | 2,799.07 | NEGATIVE is over budget, POSITIVE is under budget. |
| CPI | BCWP / ACWP 93% / 2,800 | .033 | We are getting .033 cents out of every $1. |
| SV | BCWP - BCWS 93% - 3,000 | 2,999.07 | NEGATIVE is behind schedule, POSITIVE is ahead of schedule. |
| SPI | BCWP / BCWS 93% / 3,000 | .031 | We are progressing at .031% of the rate originally planned. |
| EAC | 1,000 + 1,200 + 600 + 600 + 1,200 | 4,600 | We expect the TOTAL project to cost $4,600. |
| ETC | 600 + 1,200 | 1,800 | From this point on, we expect the project to cost $1,800 more to finish. |
| VAC | 4,600 - 4,000 | 600 | We are currently around $600 under budget. |

Given the previous, how complete is the project?  Give three answers based on the three rules presented in the slide below.