3.28   The following represent activities in Marc Massoud’s Construction Company project.

a) Draw the network to represent this situation.

b) Which activities are on the critical path?

c) What is the length of the critical path?

| Activity | Immediate Predecessor(s) | Time (weeks) | Activity | Immediate Predecessor(s) | Time (weeks) |
| --- | --- | --- | --- | --- | --- |
| A | – | 1 | E | B | 2 |
| B | – | 4 | F | C, E | 7 |
| C | A | 1 | G | D | 2 |
| D | B | 5 | H | F, G | 3 |

3.29   A small software development project at Krishna Dhir’s firm has five major activities. The times are estimated and provided in the table below. Find the expected time for completing Dhir’s project.

| Activity | Immediate Predecessor | a | m | b |
| --- | --- | --- | --- | --- |
| A | – | 2 | 5 | 8 |
| B | – | 3 | 6 | 9 |
| C | A | 4 | 7 | 10 |
| D | B | 2 | 5 | 14 |
| E | C | 3 | 3 | 3 |

a) Find the expected completion time for this project.

b) What variance value would be used to find probabilities of finishing by a certain time?