Question 2

Georgia turned in her status report for the county fair preparation activities. She feels that her pieces are on track, with nothing for you to worry about. She reports the following information for the critical path tasks:

| Task | Budgeted work/cost | Actual work/cost to date | Percent work complete | Estimate to complete | Planned Start Date | Planned End Date | Actual Start Date | Projected End date | Planned Resource Utilization/Actual Resource Utilization |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | 120 hours/$1200 | 60 hours/$600 | 30% | 90 hours/$900 | March 15 | June 15 | March 30 | June 15 | 25%/30% |
| B | 120 hours/$1200 | 50 hours/ $500 | 30% | 60 hours/ $600 | April 1 | May 15 | April 8 | May 30 | 50%/30% |

You look at her status report and determine that Georgia does not have a solid grasp of her status. Using earned value measurements along with the other information and metrics available, determine the true status of Georgia's project. Prepare an updated status report for Georgia, sharing the measurements, explaining the benefits of using EVM and rationale in your determination of the status for the project. Be sure to document some instructions for Georgia for determining the project status for her next project update to you.

Use the Library to get more information on earned value analysis and earned value management.