# LRH Marketing Project Plan

| ID | Name | Duration | Work | Start Date | Finish Date | Predecessors | Resource Names | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | LRH Marketing Project | 179.25 days | 255 days | Mon 10/23/06 | Sat 6/30/07 |  |  |  |
| 2 | Hold planning meeting | 1 day | 8 days | Mon 10/23/06 | Tue 10/24/06 |  | Sarah, Christopher, Tanya, Betty, Fred, Stan, Linda, You/PM |  |
| 3 | Get requirements from event planning team | 1 day | 2 days | Tue 10/24/06 | Wed 10/25/06 | 2 | You/PM, Linda |  |
| 4 | Logo Design | 75.5 days | 49.75 days | Wed 10/25/06 | Thu 2/8/07 |  |  |  |
| 5 | Create specs | 6.25 days | 5 days | Wed 10/25/06 | Thu 11/2/06 | 3 | Linda[30%], Betty[50%] |  |
| 6 | Create and send RFP | 3 days | 3 days | Fri 11/3/06 | Tue 11/7/06 | 5 | Purchasing |  |
| 7 | Process received bids | 0.25 days | 0.25 days | Wed 11/15/06 | Wed 11/15/06 | 6FS+5 days | Purchasing |  |
| 8 | Review bids | 8 days | 4 days | Wed 11/22/06 | Mon 12/4/06 | 7FS+5 days | Fred[50%] |  |
| 9 | Vendor selection meeting | 0.5 days | 2.5 days | Wed 12/6/06 | Wed 12/6/06 | 8FS+2 days | You/PM, Fred, Christopher, Linda, Betty |  |
| 10 | * Select Vendor | 0 days | 0 days | Wed 12/6/06 | Wed 12/6/06 | 9 | You/PM |  |
| 11 | Review Ks | 2 days | 2 days | Wed 12/6/06 | Fri 12/8/06 | 10 | Fred[75%], You/PM[50%] |  |
| 12 | Sign Vendor K | 1 day | 1 day | Thu 12/14/06 | Fri 12/15/06 | 11FS+4 days | Purchasing |  |
| 13 | Review specs with Vendor | 0.5 days | 3 days | Fri 12/15/06 | Mon 12/18/06 | 12 | Vendor A[200%], Linda[200%], Betty[200%] |  |
| 14 | Vendor prepares treatment | 8 days | 8 days | Mon 12/18/06 | Thu 12/28/06 | 13 | Vendor A |  |
| 15 | Review Treatment | 2.5 days | 5 days | Thu 12/28/06 | Mon 1/1/07 | 14 | Paul[30%], Alana[30%], Jane[30%], Sandra[30%], James[30%], You/PM[50%], Christopher[50%], Fred[75%], Betty[20%], Linda[25%] |  |
| 16 | Treatment review meeting | 0.5 days | 2.5 days | Wed 1/3/07 | Thu 1/4/07 | 15FS+2 days | Paul, Jane, Sandra, James, You/PM |  |
| 17 | Revise Treatment | 2 days | 2 days | Fri 1/5/07 | Tue 1/9/07 | 16FS+1 day | Vendor A |  |
| 18 | * Approve Treatment | 0 days | 0 days | Tue 1/9/07 | Tue 1/9/07 | 17 | Paul[30%], You/PM[50%] |  |
| 19 | Vendor prepares designs | 5 days | 5 days | Tue 1/9/07 | Tue 1/16/07 | 18 | Vendor A |  |
| 20 | Review Logo Designs | 2 days | 3 days | Wed 1/17/07 | Fri 1/19/07 | 19FS+1 day | Sarah[25%], Christopher[50%], Fred[50%], Linda[25%], Betty[50%], You/PM[50%] | Output is detailed revisions for vendor |
| 21 | Logo review meeting | 0 days | 0 days | Tue 1/23/07 | Tue 1/23/07 | 20FS+2 days | Paul, Jane, Sandra, James, Christopher, Fred, Linda, You/PM |  |
| 22 | Vendor revises logo | 2 days | 2 days | Thu 1/25/07 | Mon 1/29/07 | 21FS+2 days | Vendor A |  |
| 23 | Review revised logo | 1 day | 0.5 days | Thu 2/1/07 | Fri 2/2/07 | 22FS+3 days | You/PM[50%] |  |
| 24 | Vendor revises logo second time | 1 day | 1 day | Wed 2/7/07 | Thu 2/8/07 | 23FS+3 days | Vendor A |  |
| 25 | * OK for Logo | 0 days | 0 days | Thu 2/8/07 | Thu 2/8/07 | 24 | You/PM[50%] |  |
| 26 | Spokesperson Commitments | 23 days | 7 days | Fri 3/2/07 | Wed 4/4/07 |  |  |  |
| 27 | Select spokesperson | 10 days | 5 days | Fri 3/2/07 | Fri 3/16/07 | 3 | Linda[25%], You/PM[50%] |  |
| 28 | Verify date commitments | 2 days | 0.5 days | Fri 3/16/07 | Tue 3/20/07 | 27, 63, 105 | Linda[25%] | Dependent on reserving the shoot site and the golf course so dates can go into contract. |
| 29 | Sign spokesperson K | 1 day | 1.5 days | Tue 4/3/07 | Wed 4/4/07 | 28FS+10 days | Purchasing, Smith |  |
| 30 | * Spokesperson on board | 0 days | 0 days | Wed 4/4/07 | Wed 4/4/07 | 29 |  |  |
| 31 | Web Page | 91.5 days | 29.75 days | Fri 2/16/07 | Mon 6/25/07 |  |  |  |
| 32 | Gather Information | 4 days | 2 days | Fri 2/16/07 | Thu 2/22/07 | 3 | Stan[25%], You/PM[50%] |  |
| 33 | Write copy | 6 days | 3 days | Thu 2/22/07 | Fri 3/2/07 | 32, 62 | Betty[50%] | Dependent on completing the media buy so you know the lengths of spots etc. |
| 34 | Review and Approve copy | 2 days | 1 day | Mon 3/5/07 | Wed 3/7/07 | 33FS+1 day | You/PM[50%] |  |
| 35 | Design Web Page (prototype) | 12 days | 3 days | Wed 3/7/07 | Fri 3/23/07 | 34 | Stan[25%] |  |
| 36 | Review Web Page | 4 days | 6 days | Fri 3/23/07 | Thu 3/29/07 | 35 | Sarah[25%], Christopher[50%], Betty[50%], Fred[50%], Linda[25%], You/PM[50%] |  |
| 37 | Web Page review meeting | 0.5 days | 4 days | Thu 3/29/07 | Thu 3/29/07 | 36 | Paul, Jane, Sandra, James, Christopher, Fred, Linda, You/PM |  |
| 38 | Revisions to Web Page | 4 days | 1 day | Tue 4/3/07 | Fri 4/6/07 | 37FS+2 days | Stan[25%] |  |
| 39 | OK for Web Page design | 1 day | 0.5 days | Tue 4/10/07 | Tue 4/10/07 | 38FS+1 day | You/PM[50%] |  |
| 40 | Send logo to Web Page Designer | 1 day | 1 day | Wed 4/11/07 | Wed 4/11/07 | 39, 25 | Vendor A | Dependent on completion of logo |
| 41 | Add logo to web page | 1 day | 0.25 days | Thu 4/12/07 | Thu 4/12/07 | 40 | Stan[25%] |  |
| 42 | Send still photos to web page developer | 1 day | 1 day | Fri 4/13/07 | Fri 4/13/07 | 109FS+1 day, 41 | Vendor C | Dependent on completion of still photos |
| 43 | Add still photos | 2 days | 0.5 days | Mon 4/16/07 | Tue 4/17/07 | 42 | Stan[25%] |  |
| 44 | QA web page | 4 days | 1 day | Wed 4/18/07 | Mon 4/23/07 | 43, 41 | Stan[25%] |  |
| 45 | Put web page on online | 1 day | 0.25 days | Tue 4/24/07 | Tue 4/24/07 | 44 | Stan[25%] |  |
| 46 | * Initial Web Page Complete | 0 days | 0 days | Wed 4/25/07 | Wed 4/25/07 | 45 |  |  |
| 47 | Update Web Page (1) | 7 days | 2.5 days | Wed 5/9/07 | Thu 5/17/07 |  |  |  |
| 48 | Write copy | 4 days | 2 days | Wed 5/9/07 | Mon 5/14/07 | 46FS+10 days | Betty[50%] |  |
| 49 | Add to web page | 2 days | 0.5 days | Tue 5/15/07 | Wed 5/16/07 | 48 | Stan[25%] |  |
| 50 | * Update complete | 1 day | 0 days | Thu 5/17/07 | Thu 5/17/07 | 49 |  |  |
| 51 | Update Web Page (2) | 3 days | 1.25 days | Fri 6/1/07 | Wed 6/6/07 |  |  |  |
| 52 | Write copy | 2 days | 1 day | Fri 6/1/07 | Mon 6/4/07 | 50FS+10 days | Betty[50%] |  |
| 53 | Add to web page | 1 day | 0.25 days | Tue 6/5/07 | Tue 6/5/07 | 52 | Stan[25%] |  |
| 54 | * Update complete | 0 days | 0 days | Wed 6/6/07 | Wed 6/6/07 | 53 |  |  |
| 55 | Update Web Page (3) | 4 days | 1.5 days | Wed 6/20/07 | Mon 6/25/07 |  |  |  |
| 56 | Write copy | 2 days | 1 day | Wed 6/20/07 | Thu 6/21/07 | 54FS+10 days | Betty[50%] |  |
| 57 | Add to web page | 2 days | 0.5 days | Fri 6/22/07 | Mon 6/25/07 | 56 | Stan[25%] |  |
| 58 | * Update complete | 0 days | 0 days | Mon 6/25/07 | Mon 6/25/07 | 57 |  |  |
| 59 | Video Shoot for TV spot | 116 days | 49.25 days | Fri 1/19/07 | Sat 6/30/07 |  |  |  |
| 60 | Determine times and length | 4 days | 1 day | Fri 1/19/07 | Wed 1/24/07 | 3 | Linda[25%] |  |
| 61 | Write script | 5 days | 5 days | Thu 1/25/07 | Wed 1/31/07 | 60 | Vendor B |  |
| 62 | Do media buy | 4 days | 1 day | Fri 1/26/07 | Wed 1/31/07 | 60 | Linda[25%] |  |
| 63 | Reserve shoot site | 4 days | 1 day | Fri 1/26/07 | Wed 1/31/07 | 60 | Linda[25%] |  |
| 64 | Review script | 4 days | 4 days | Thu 2/1/07 | Tue 2/6/07 | 61, 63, 62 | Linda[25%], Fred[50%], You/PM[50%], Betty[50%] | Dependency on Writing Script, Doing media buy, and reserving the shoot site |
| 65 | Script Review Meeting | 0.5 days | 2.5 days | Fri 2/9/07 | Fri 2/9/07 | 64FS+2 days | Paul, Jane, Sandra, James, You/PM |  |
| 66 | Script revisions | 3 days | 3 days | Mon 2/12/07 | Thu 2/15/07 | 65FS+1 day | Vendor B |  |
| 67 | Review revised script | 8 days | 8 days | Thu 2/15/07 | Tue 2/27/07 | 66 | Linda[25%], Fred[50%], You/PM[50%], Betty[50%] |  |
| 68 | * Approve script | 0 days | 0 days | Tue 2/27/07 | Tue 2/27/07 | 67 | You/PM[50%] |  |
| 69 | Design graphics et al | 25 days | 5 days | Tue 2/27/07 | Tue 4/3/07 | 68 | Fred[10%], Sarah[25%] |  |
| 70 | Review design | 2 days | 2 days | Tue 4/3/07 | Thu 4/5/07 | 69 | Linda[25%], You/PM[50%], Fred[50%], Betty[50%] |  |
| 71 | Add logo | 1 day | 0.25 days | Thu 4/5/07 | Fri 4/6/07 | 70, 25 | Sarah[25%] | Dependent on completion of logo |
| 72 | Graphic design review meeting | 0.5 days | 2.5 days | Tue 4/10/07 | Tue 4/10/07 | 71FS+2 days | Paul, Jane, Sandra, James, You/PM |  |
| 73 | Revise graphics | 8 days | 2 days | Thu 4/12/07 | Mon 4/23/07 | 72FS+1 day | Sarah[25%] |  |
| 74 | Review revised graphics | 0.5 days | 0.5 days | Tue 4/24/07 | Tue 4/24/07 | 73 | You/PM[50%], Fred[50%] |  |
| 75 | * Approve Graphics | 0 days | 0 days | Tue 4/24/07 | Tue 4/24/07 | 74 | You/PM[50%] |  |
| 76 | Shoot video | 1 day | 3 days | Tue 4/24/07 | Wed 4/25/07 | 75, 63, 30 | Linda, Betty, Smith |  |
| 77 | Edit video | 1 day | 3 days | Thu 4/26/07 | Fri 4/27/07 | 76FS+1 day | Linda, Vendor B, Betty |  |
| 78 | Video review meeting | 0.5 days | 2.5 days | Tue 5/1/07 | Tue 5/1/07 | 77FS+2 days | Paul, Jane, Sandra, James, You/PM |  |
| 79 | Video revisions | 2 days | 2 days | Thu 5/3/07 | Fri 5/4/07 | 78FS+1 day | Vendor B |  |
| 80 | * Approve final video | 0 days | 0 days | Tue 5/8/07 | Tue 5/8/07 | 79FS+1 day | You/PM[50%] |  |
| 81 | Deliver video to TV stations | 4 days | 1 day | Wed 5/9/07 | Mon 5/14/07 | 80FS+1 day | Linda[25%] |  |
| 82 | Air Video Commercials | 34 days | 0 days | Tue 5/15/07 | Sat 6/30/07 | 81 |  |  |
| 83 | Air Video Commercials 1 | 10 mins | 0 days | Tue 5/15/07 | Tue 5/15/07 |  |  |  |
| 84 | Air Video Commercials 2 | 0 mins | 0 days | Sat 5/19/07 | Sat 5/19/07 |  |  |  |
| 85 | Air Video Commercials 3 | 0 mins | 0 days | Sun 5/20/07 | Sun 5/20/07 |  |  |  |
| 86 | Air Video Commercials 4 | 480 mins | 0 days | Tue 5/22/07 | Tue 5/22/07 |  |  |  |
| 87 | Air Video Commercials 5 | 0 mins | 0 days | Sat 5/26/07 | Sat 5/26/07 |  |  |  |
| 88 | Air Video Commercials 6 | 0 mins | 0 days | Sun 5/27/07 | Sun 5/27/07 |  |  |  |
| 89 | Air Video Commercials 7 | 10 mins | 0 days | Tue 5/29/07 | Tue 5/29/07 |  |  |  |
| 90 | Air Video Commercials 8 | 0 mins | 0 days | Sat 6/2/07 | Sat 6/2/07 |  |  |  |
| 91 | Air Video Commercials 9 | 0 mins | 0 days | Sun 6/3/07 | Sun 6/3/07 |  |  |  |
| 92 | Air Video Commercials 10 | 10 mins | 0 days | Tue 6/5/07 | Tue 6/5/07 |  |  |  |
| 93 | Air Video Commercials 11 | 10 mins | 0 days | Sat 6/9/07 | Mon 6/11/07 |  |  |  |
| 94 | Air Video Commercials 12 | 10 mins | 0 days | Sun 6/10/07 | Mon 6/11/07 |  |  |  |
| 95 | Air Video Commercials 13 | 10 mins | 0 days | Tue 6/12/07 | Tue 6/12/07 |  |  |  |
| 96 | Air Video Commercials 14 | 10 mins | 0 days | Sat 6/16/07 | Mon 6/18/07 |  |  |  |
| 97 | Air Video Commercials 15 | 10 mins | 0 days | Sun 6/17/07 | Mon 6/18/07 |  |  |  |
| 98 | Air Video Commercials 16 | 10 mins | 0 days | Tue 6/19/07 | Tue 6/19/07 |  |  |  |
| 99 | Air Video Commercials 17 | 10 mins | 0 days | Sat 6/23/07 | Mon 6/25/07 |  |  |  |
| 100 | Air Video Commercials 18 | 10 mins | 0 days | Sun 6/24/07 | Mon 6/25/07 |  |  |  |
| 101 | Air Video Commercials 19 | 10 mins | 0 days | Tue 6/26/07 | Tue 6/26/07 |  |  |  |
| 102 | Air Video Commercials 20 | 0 mins | 0 days | Sat 6/30/07 | Sat 6/30/07 |  |  |  |
| 103 | Photo Shoot for stills | 68 days | 16.25 days | Fri 3/9/07 | Wed 6/13/07 |  |  |  |
| 104 | Prepare requirements | 4 days | 5 days | Fri 3/9/07 | Thu 3/15/07 | 3 | Fred[50%], Betty[50%], Linda[25%] |  |
| 105 | Reserve golf course for shoot | 1 day | 0.25 days | Thu 3/15/07 | Fri 3/16/07 | 104 | Linda[25%] |  |
| 106 | Shoot | 1 day | 3 days | Wed 4/4/07 | Thu 4/5/07 | 105, 30 | Vendor C, Betty, Smith | Dependent on spokesperson on board |
| 107 | Review proofs | 1 day | 1.5 days | Thu 4/5/07 | Fri 4/6/07 | 106 | Fred[50%], You/PM[50%], Betty[50%] |  |
| 108 | Proof review meeting | 0.5 days | 2.5 days | Tue 4/10/07 | Tue 4/10/07 | 107FS+2 days | Paul, Jane, Sandra, James, You/PM |  |
| 109 | * Approve proofs | 0 days | 0 days | Thu 4/12/07 | Thu 4/12/07 | 108FS+1 day | You/PM[50%] |  |
| 110 | Produce print and jpeg copies | 4 days | 4 days | Thu 6/7/07 | Wed 6/13/07 | 109 | Vendor B |  |
| 111 | Merchandise | 39.4 days | 36.5 days | Mon 5/7/07 | Fri 6/29/07 |  |  |  |
| 112 | Create specs | 2.4 days | 3 days | Mon 5/7/07 | Wed 5/9/07 | 3 | Linda[25%], Fred[50%], You/PM[50%] |  |
| 113 | Spec review meeting | 0.5 days | 2.5 days | Fri 5/11/07 | Fri 5/11/07 | 112FS+1 day | Paul, Jane, Sandra, James, You/PM |  |
| 114 | Get bids | 1 day | 1 day | Mon 5/14/07 | Tue 5/15/07 | 113FS+1 day | Purchasing |  |
| 115 | Review bids | 4 days | 3 days | Tue 5/22/07 | Mon 5/28/07 | 114FS+5 days | Linda[25%], Fred[75%], You/PM[50%] |  |
| 116 | Select Vendors | 2 days | 1.5 days | Mon 5/28/07 | Wed 5/30/07 | 115 | You/PM[50%], Linda[25%], Fred[75%] | One vendor for each type of merchandise |
| 117 | Sign vendor Ks | 1 day | 1 day | Thu 5/31/07 | Fri 6/1/07 | 116FS+1 day | Purchasing |  |
| 118 | Send vendors logo | 2 days | 0.5 days | Wed 6/13/07 | Fri 6/15/07 | 25, 117FS+1 day | Linda[25%] | Dependent on logo completion |
| 119 | Send t-shirt vendor photos | 2 days | 0.5 days | Wed 6/13/07 | Fri 6/15/07 | 117FS+1 day, 110 | Linda[25%] | Dependent on completion of still photos |
| 120 | Baseball caps | 13.83 days | 5 days | Fri 6/8/07 | Thu 6/28/07 |  |  |  |
| 121 | Select Baseball caps | 1.33 days | 1 day | Fri 6/8/07 | Mon 6/11/07 | 117FS+2 days | Linda[25%], Fred[50%] | Dependent on vendor contracts |
| 122 | Process order and send to vendor | 1 day | 1 day | Wed 6/13/07 | Thu 6/14/07 | 121FS+2 days | Purchasing |  |
| 123 | Vendor produces baseball caps | 1 day | 1 day | Thu 6/14/07 | Fri 6/15/07 | 122 | Vendor D |  |
| 124 | Receive baseball caps | 0.5 days | 0.5 days | Fri 6/22/07 | Fri 6/22/07 | 123FS+5 days | Purchasing |  |
| 125 | QA Baseball caps | 2 days | 1.5 days | Tue 6/26/07 | Wed 6/27/07 | 124FS+1 day | Fred[50%], Linda[25%], You/PM[50%] |  |
| 126 | * OK Baseball caps | 0 days | 0 days | Thu 6/28/07 | Thu 6/28/07 | 125 | You/PM[50%] |  |
| 127 | T Shirts | 12.83 days | 9.5 days | Mon 6/11/07 | Thu 6/28/07 |  |  |  |
| 128 | Select tees | 1.33 days | 1 day | Mon 6/11/07 | Tue 6/12/07 | 117FS+2 days | Linda[25%], Betty[50%] | Dependent on vendor contracts |
| 129 | Send order to Purchasing | 1 day | 1 day | Tue 6/12/07 | Wed 6/13/07 | 128 | Fred |  |
| 130 | Process order and send to vendor | 1 day | 1 day | Thu 6/14/07 | Fri 6/15/07 | 129FS+1 day | Purchasing |  |
| 131 | Vendor prints tees | 5 days | 5 days | Fri 6/15/07 | Fri 6/22/07 | 130, 119, 118 | Vendor D |  |
| 132 | Receive T-shirts | 0.5 days | 0.5 days | Mon 6/25/07 | Mon 6/25/07 | 131FS+1 day | Purchasing |  |
| 133 | QA Tees | 1 day | 1 day | Wed 6/27/07 | Wed 6/27/07 | 132FS+1 day | Fred |  |
| 134 | * OK Tees | 0 days | 0 days | Thu 6/28/07 | Thu 6/28/07 | 133 | You/PM[50%] |  |
| 135 | Key chains | 16.5 days | 8 days | Tue 6/5/07 | Wed 6/27/07 |  |  |  |
| 136 | Select key chain | 1 day | 1 day | Tue 6/5/07 | Wed 6/6/07 | 117FS+2 days | Linda[25%], Tanya[75%] | Dependent on vendor contracts... |
| 137 | Meet with Vendor | 1 day | 1 day | Wed 6/6/07 | Thu 6/7/07 | 136 | Fred |  |
| 138 | Send order to Purchasing | 1 day | 1 day | Thu 6/7/07 | Fri 6/8/07 | 137 | Fred |  |
| 139 | Process order and send to vendor | 1 day | 1 day | Mon 6/11/07 | Tue 6/12/07 | 138FS+1 day | Purchasing |  |
| 140 | Vendor produces key chains | 2 days | 2 days | Tue 6/12/07 | Thu 6/14/07 | 139 | Vendor E |  |
| 141 | Receive key chains | 1 day | 1 day | Thu 6/21/07 | Fri 6/22/07 | 140FS+5 days | Purchasing |  |
| 142 | QA key chains | 0.5 days | 0.5 days | Mon 6/25/07 | Mon 6/25/07 | 141FS+1 day | Fred | Experience suggests low likelihood of errors in the keys; therefore no need for revision cycle |
| 143 | * Accept key chains | 2 days | 0.5 days | Tue 6/26/07 | Wed 6/27/07 | 142 | Linda[25%] |  |
| 144 | Deliver merchandise to golf course | 1 day | 0 days | Fri 6/29/07 | Fri 6/29/07 | 126FS+1 day, 143FS+1 day, 134FS+1 day |  | Dependent on completion of caps, tee shirts and key chains |
| 145 | Set up merchandise at course | 1 day | 1 day | Fri 6/29/07 | Fri 6/29/07 | 144FS+1 day | Fred |  |
| 146 | Brochures | 120.92 days | 24.75 days | Fri 1/12/07 | Fri 6/29/07 |  |  |  |
| 147 | Locate and sign distributor | 2 days | 0.5 days | Fri 1/12/07 | Tue 1/16/07 | 3 | Linda[25%] |  |
| 148 | Design brochure | 4 days | 3 days | Tue 1/16/07 | Mon 1/22/07 | 147 | Linda[25%], Fred[50%] |  |
| 149 | Design Review Meeting | 0.5 days | 2.5 days | Wed 1/24/07 | Wed 1/24/07 | 148FS+2 days | Paul, Jane, Sandra, James, You/PM |  |
| 150 | Write copy | 5 days | 5 days | Wed 1/24/07 | Wed 1/31/07 | 149 | Linda[25%], Tanya[75%] |  |
| 151 | Revise design | 4 days | 2 days | Wed 1/31/07 | Tue 2/6/07 | 150 | Fred[50%] |  |
| 152 | * Approve brochure design | 0 days | 0 days | Tue 2/6/07 | Tue 2/6/07 | 151 | You/PM[50%] |  |
| 153 | Send brochure design to vendor | 0.67 days | 0.5 days | Wed 2/7/07 | Thu 2/8/07 | 152FS+1 day | Tanya[75%] |  |
| 154 | Add stills | 0.25 days | 0.25 days | Fri 6/29/07 | Fri 6/29/07 | 153, 110 | Vendor F |  |
| 155 | Add logo | 0.25 days | 0.25 days | Thu 2/8/07 | Thu 2/8/07 | 25, 153 | Vendor F | Dependent on completion of logo |
| 156 | Create brochure galleys | 5 days | 5 days | Thu 2/8/07 | Thu 2/15/07 | 155 | Vendor F |  |
| 157 | Review galleys | 0.5 days | 0.75 days | Thu 2/15/07 | Thu 2/15/07 | 156 | Linda[50%], Fred[50%], You/PM[50%] |  |
| 158 | Revise galleys | 2 days | 2 days | Mon 2/19/07 | Tue 2/20/07 | 157FS+1 day | Vendor F |  |
| 159 | Print brochures | 1 day | 1 day | Fri 2/23/07 | Fri 2/23/07 | 158FS+2 days | Vendor F |  |
| 160 | Review printed brochures | 1 day | 1.5 days | Mon 2/26/07 | Mon 2/26/07 | 159 | Linda[50%], Fred[50%], You/PM[50%] |  |
| 161 | * Accept brochures | 0 days | 0 days | Tue 2/27/07 | Tue 2/27/07 | 160 | You/PM |  |
| 162 | Send brochures to distributor | 2 days | 0.5 days | Wed 2/28/07 | Thu 3/1/07 | 161FS+1 day | Linda[25%] |  |
| 163 | Distribute brochures | 21 days | 0 days | Fri 3/2/07 | Fri 3/30/07 | 162 |  |  |
| 164 | Distribute brochures 1 | 1 day | 0 days | Fri 3/2/07 | Fri 3/2/07 |  |  |  |
| 165 | Distribute brochures 2 | 1 day | 0 days | Fri 3/9/07 | Fri 3/9/07 |  |  |  |
| 166 | Distribute brochures 3 | 1 day | 0 days | Fri 3/16/07 | Fri 3/16/07 |  |  |  |
| 167 | Distribute brochures 4 | 1 day | 0 days | Fri 3/23/07 | Fri 3/23/07 |  |  |  |
| 168 | Distribute brochures 5 | 1 day | 0 days | Fri 3/30/07 | Fri 3/30/07 |  |  |  |
| 169 | Outdoor Signage | 113.9 days | 31.75 days | Tue 1/23/07 | Fri 6/29/07 |  |  |  |
| 170 | Create specs | 2.4 days | 3 days | Tue 1/23/07 | Thu 1/25/07 | 3 | Fred[50%], Linda[25%], You/PM[50%] |  |
| 171 | Get bids | 1 day | 1 day | Thu 1/25/07 | Fri 1/26/07 | 170 | Purchasing |  |
| 172 | Receive bids | 0.5 days | 0.5 days | Fri 2/2/07 | Fri 2/2/07 | 171FS+5 days | Purchasing |  |
| 173 | Review bids | 4 days | 3 days | Tue 2/6/07 | Fri 2/9/07 | 172FS+1 day | Fred[50%], Linda[25%], You/PM[50%] |  |
| 174 | Select Vendor | 4 days | 2 days | Mon 2/19/07 | Thu 2/22/07 | 173FS+5 days | Fred[50%] |  |
| 175 | Draft K | 1 day | 1 day | Fri 2/23/07 | Fri 2/23/07 | 174 | Purchasing |  |
| 176 | Review K | 1 day | 1 day | Mon 2/26/07 | Mon 2/26/07 | 175 | Fred[50%], You/PM[50%] |  |
| 177 | Sign Vendor K | 0.5 days | 0.5 days | Mon 3/5/07 | Mon 3/5/07 | 176FS+4 days | Purchasing |  |
| 178 | Review specs with Vendor | 0.5 days | 0.5 days | Mon 3/5/07 | Mon 3/5/07 | 177 | Fred |  |
| 179 | Send vendor logo | 1 day | 0.5 days | Tue 3/6/07 | Tue 3/6/07 | 178, 25 | Fred[50%] | Dependent on completion of logo |
| 180 | Vendor produces signage | 10 days | 10 days | Wed 5/30/07 | Wed 6/13/07 | 179 | Vendor G |  |
| 181 | Receive signage | 0.25 days | 0.25 days | Wed 6/13/07 | Wed 6/13/07 | 180 | Purchasing |  |
| 182 | QA signage | 2 days | 2 days | Thu 6/14/07 | Mon 6/18/07 | 181FS+1 day | Linda[50%], Fred[67%] |  |
| 183 | Send Vendor changes | 2 hrs | 0.25 days | Mon 6/18/07 | Mon 6/18/07 | 182 | Fred |  |
| 184 | Vendor does revisions | 5 days | 5 days | Tue 6/19/07 | Tue 6/26/07 | 183FS+1 day | Vendor G |  |
| 185 | Received new signage | 0.25 days | 0.25 days | Tue 6/26/07 | Tue 6/26/07 | 184 | Purchasing |  |
| 186 | * Approve signage | 0 days | 0 days | Thu 6/28/07 | Thu 6/28/07 | 185FS+1 day | You/PM[50%], Fred |  |
| 187 | Post signage at golf course | 1 day | 1 day | Fri 6/29/07 | Fri 6/29/07 | 186FS+1 day | Vendor G | Post day before tournament |
| 188 | Golf Tournament | 0 days | 0 days | Sat 6/30/07 | Sat 6/30/07 | 187 |  |  |