# LRH Marketing Project Plan

| ID | Name | Duration | Work | Start Date | Finish Date | Predecessors | Resource Names | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | LRH Marketing Project | 179.25 days | 255 days | Mon 10/23/06 | Sat 6/30/07 |  |  |  |
| 2 | Hold planning meeting | 1 day | 8 days | Mon 10/23/06 | Tue 10/24/06 |  | Sarah, Christopher, Tanya, Betty, Fred, Stan, Linda, You/PM |  |
| 3 | Get requirements from event planning team | 1 day | 2 days | Tue 10/24/06 | Wed 10/25/06 | 2 | You/PM, Linda |  |
| 4 | Logo Design | 75.5 days | 49.75 days | Wed 10/25/06 | Thu 2/8/07 |  |  |  |
| 26 | Spokesperson Commitments | 23 days | 7 days | Fri 3/2/07 | Wed 4/4/07 |  |  |  |
| 31 | Web Page | 91.5 days | 29.75 days | Fri 2/16/07 | Mon 6/25/07 |  |  |  |
| 47 | Update Web Page (1) | 7 days | 2.5 days | Wed 5/9/07 | Thu 5/17/07 |  |  |  |
| 51 | Update Web Page (2) | 3 days | 1.25 days | Fri 6/1/07 | Wed 6/6/07 |  |  |  |
| 55 | Update Web Page (3) | 4 days | 1.5 days | Wed 6/20/07 | Mon 6/25/07 |  |  |  |
| 59 | Video Shoot for TV spot | 116 days | 49.25 days | Fri 1/19/07 | Sat 6/30/07 |  |  |  |
| 82 | Air Video Commercials | 34 days | 0 days | Tue 5/15/07 | Sat 6/30/07 | 81 |  |  |
| 103 | Photo Shoot for stills | 68 days | 16.25 days | Fri 3/9/07 | Wed 6/13/07 |  |  |  |
| 111 | Merchandise | 39.4 days | 36.5 days | Mon 5/7/07 | Fri 6/29/07 |  |  |  |
| 120 | Baseball caps | 13.83 days | 5 days | Fri 6/8/07 | Thu 6/28/07 |  |  |  |
| 127 | T Shirts | 12.83 days | 9.5 days | Mon 6/11/07 | Thu 6/28/07 |  |  |  |
| 135 | Key chains | 16.5 days | 8 days | Tue 6/5/07 | Wed 6/27/07 |  |  |  |
| 146 | Brochures | 120.92 days | 24.75 days | Fri 1/12/07 | Fri 6/29/07 |  |  |  |
| 163 | Distribute brochures | 21 days | 0 days | Fri 3/2/07 | Fri 3/30/07 | 162 |  |  |
| 169 | Outdoor Signage | 113.9 days | 31.75 days | Tue 1/23/07 | Fri 6/29/07 |  |  |  |
| 188 | Golf Tournament | 0 days | 0 days | Sat 6/30/07 | Sat 6/30/07 | 187 |  |  |