- St. Andrews Academy is considering building a new multipurpose athletic complex on campus.  The complex would provide a new gymnasium for basketball games, expanded office space, classrooms, and intramural facilities.  The following activities would have to be undertaken before construction can begin.

| Activity | Description | Immediate Predecessor | Time (weeks) |
| --- | --- | --- | --- |
| A | Survey building site | -- | 6 |
| B | Develop initial design | -- | 8 |
| C | Obtain board approval | A, B | 12 |
| D | Select architect | C | 4 |
| E | Establish budget | C | 6 |
| F | Finalize design | D, E | 15 |
| G | Obtain financing | E | 12 |
| H | Hire contractor | F, G | 8 |

- Prepare a project network.

- Develop the activity schedule for the project.

- Identify the critical path.

- Does it appear reasonable that construction of the athletic complex could begin one year after the decision to begin the project with the site survey and initial design plans?

- What is the expected completion time for the project?