1.Project Network

| Activity | Expected Time | Variance |
| --- | --- | --- |
| A | 6 | 0.44 |
| B | 9 | 2.78 |
| C | 4 | 0.44 |
| D | 12 | 7.11 |
| E | 10 | 1.00 |
| F | 6 | 0.44 |
| G | 8 | 7.11 |
| H | 6 | 0.44 |
| I | 7 | 2.78 |
| J | 4 | 0.11 |
| K | 4 | 0.44 |

| Activity | Earliest Start | Latest Start | Earliest Finish | Latest Finish | Slack | Critical Activity |
| --- | --- | --- | --- | --- | --- | --- |
| A | 0 | 3 | 6 | 9 | 3 |  |
| B | 0 | 0 | 9 | 9 | 0 | Yes |
| C | 9 | 9 | 13 | 13 | 0 | Yes |
| D | 13 | 17 | 25 | 29 | 4 |  |
| E | 13 | 13 | 23 | 23 | 0 | Yes |
| F | 23 | 23 | 29 | 29 | 0 | Yes |
| G | 13 | 21 | 21 | 29 | 8 |  |
| H | 29 | 29 | 35 | 35 | 0 | Yes |
| I | 29 | 32 | 36 | 39 | 3 |  |
| J | 35 | 35 | 39 | 39 | 0 | Yes |
| K | 39 | 39 | 43 | 43 | 0 | Yes |

The expected project completion time is 43 weeks.  The critical path activities are B-C-E-F-H-J-K.  The variance of the critical path is 5.67.

Area = 0.3962

P(T  40) = 0.5000 - 0.3962 = 0.1038

Given the above calculations, we can conclude that there is about a 10% chance that the project can be completed in 40 weeks or less.  Coleman should consider crashing project activities.

2.

For 80% chance,

z = +0.84

Thus

Solve for E(T) = 38 weeks.

R.C. Coleman should crash activities to reduce the expected project completion time to 38 weeks.

3.	In this section, we will use expected activity times as normal times and use a linear programming model based on expected times to make the crashing decisions.

Let	xi = the completion time for activity i

yi = the amount of crash time for activity i

Min	450yA  +  400yB  +  600yC  +  300yD  +  1000yE  +  550yF  +  750yG  +  700yH  +  800yI  + 400yJ  +  500yK

s.t.

| xA + yA  6 xB + yB  9 xC + yC – xA  4 xC + yC – xB  4 xD + yD – xC  12 xE + yE – xC  10 xF + yF – xE  6 xG + yG – xC  8 xH + yH – xF  6 xH + yH – xG  6 xI + yI – xD  7 xI + yI – xF  7 xJ + yJ – xH  4 xK + yK – xI  4 xK + yK – xJ  4 | xK  38 yA  2 yB  2 yC  2 yD  4 yE  3 yF  2 yG  3 yH  2 yI  3 yJ  1 yK  1 All xi,yi  0 |
| --- | --- |

The optimal crashing decisions are as follows:

| Crash Activity | Weeks | Cost |
| --- | --- | --- |
| B | 2 | 800 |
| F | 1 | 550 |
| J | 1 | 400 |
| K | 1 | 500 |
|  | Total | 2250 |

A revised activity schedule based on these crashing decisions is as follows:

| Activity | Earliest Start | Latest Start | Earliest Finish | Latest Finish | Slack | Critical Activity |
| --- | --- | --- | --- | --- | --- | --- |
| A | 0 | 1 | 6 | 7 | 1 |  |
| B | 0 | 0 | 7 | 7 | 0 | Yes |
| C | 7 | 7 | 11 | 11 | 0 | Yes |
| D | 11 | 14 | 23 | 26 | 3 |  |
| E | 11 | 11 | 21 | 21 | 0 | Yes |
| F | 21 | 21 | 26 | 26 | 0 | Yes |
| G | 11 | 18 | 19 | 26 | 7 |  |
| H | 26 | 26 | 32 | 32 | 0 | Yes |
| I | 26 | 28 | 33 | 35 | 2 |  |
| J | 32 | 32 | 35 | 35 | 0 | Yes |
| K | 35 | 35 | 38 | 38 | 0 | Yes |

The student should comment on the fact that the crashing decisions may alter the variance in the project completion time.  By defining revised optimistic, most probable, and pessimistic times for crashed activities B, F, J, and K, a revised variance in the project completion time can be found.  Using this result, a revised probability of a 40-week completion time can be computed.