Use the following info

|  |  |  |
| --- | --- | --- |
| Activity | Activity time(weeks) | Immediate Predecessor(s) |
| A | 3 | NONE |
| B | 4 | A |
| C | 2 | B |
| D | 5 | B |
| E | 4 | C |
| F | 3 | D |
| G | 2 | E,F |
|  |  |  |

1. Construct a network diagram using AON notation
2. Using the network diagram constructed in question 1
3. Calculate the completion time for the project
4. Determine which activities are included on the critical path