## Gantt
ERP IMPLEMENTATION
S. No | Task Name | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Preparation | bar: Q1 Jan
1.1 | Define project scope and objectives
1.2 | Identify Project team
1.3 | Business blueprint
2 | System architecture design | bar: Q1 Feb to Q1 Mar
2.1 | Identify system environment
2.1.1 | Technical infrastructure preparation
2.1.2 | Identify development environment
2.1.3 | Identify training environement
2.1.4 | Identify production environment
3 | Business blueprint | bar: Q1 Feb to Q2 Apr
3.1 | AS-IS business process analysis
3.1.1 | Identify end-to-end current business processes
3.1.2 | Identify process integrator points
3.1.3 | Define end-to-end future business processes
3.2 | Map ERP to business processes
3.3 | Define TO-BE processes
3.4 | Identify and resolve Gaps
3.5 | Document blueprint
3.6 | Sign-off blueprint
4 | Configuration and development | bar: Q2 Apr to Q3 Jul
4.1 | Configurator solution
4.1.1 | Unit test scripts
4.1.2 | Configure solution
4.1.3 | Unit test configuration
4.2 | Develop code for identified gaps
4.2.1 | Technical specification
4.2.2 | Unit test scripts
4.3 | Sign off configuration
5 | Data conversion | bar: Q3 Sep
5.1 | Map ERP fields to legacy system fields
6 | System Testing | bar: Q4 Oct
6.1 | Define test scripts
6.2 | Perform end-to-end testing
6.3 | Sign-off system testing
7 | Training | bar: Q4 Oct to Q4 Nov
7.1 | Develop training plan
7.2 | Document training
7.3 | Train users on business processes
7.4 | Train users on ERP
8 | User acceptance testing | bar: Q4 Nov to Q4 Dec
9 | Cutover | bar: Q4 Nov to Q4 Dec
9.1 | Migrate data from legacy system to ERP
9.2 | Go Live

## Budget schedule
BUDGET SCHEDULE
| Task | Budget Deviation | Schedule Deviation | Estimate Total | Actual Total
1 | Preparation | 2500 | -2 | 3000 | 4000
1.1 | Define project scope and objectives
1.2 | Identify Project team
1.3 | Business blueprint
2 | System architecture design | 5000 | -1 | 5500 | 6000
2.1 | Identify system environment
2.1.1 | Technical infrastructure preparation
2.1.2 | Identify development environment
2.1.3 | Identify training environement
2.1.4 | Identify production environment
3 | Business blueprint | 30000 | -5 | 35000 | 40000
3.1 | AS-IS business process analysis
3.1.1 | Identify end-to-end current business processes
3.1.2 | Identify process integrator points
3.1.3 | Define end-to-end future business processes
3.2 | Map ERP to business processes
3.3 | Define TO-BE processes
3.4 | Identify and resolve Gaps
3.5 | Document blueprint
3.6 | Sign-off blueprint
4 | Configuration and development | 100000 | -7 | 120000 | 125000
4.1 | Configurator solution
4.1.1 | Unit test scripts
4.1.2 | Configure solution
4.1.3 | Unit test configuration
4.2 | Develop code for identified gaps
4.2.1 | Technical specification
4.2.2 | Unit test scripts
4.3 | Sign off configuration
5 | Data conversion | 25000 | -1 | 25000 | 25000
5.1 | Map ERP fields to legacy system fields
6 | System Testing | 10000 | 0 | 9000 | 12000
6.1 | Define test scripts
6.2 | Perform end-to-end testing
6.3 | Sign-off system testing
7 | Training | 25000 | 0 | 30000 | 30000
7.1 | Develop training plan
7.2 | Document training
7.3 | Train users on business processes
7.4 | Train users on ERP
8 | User acceptance testing | 5000 | 0 | 5000 | 6000
9 | Cutover | 8000 | -1 | 9000 | 11000
9.1 | Migrate data from legacy system to ERP
9.2 | Go Live