b. WORK BREAKDOWN SCHEDULE (WBS)

|  | Work Breakdown Structure for CDGA |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Project: Johnson Family 3-car Garage w/living quarters |  |  |  |
| WBS Code | Task/Subtask | Duration | Milestones | Who |  |  |
| 1 | Remove Trees from site | 2 Days |  | Johnson |  |  |
| 2 | Draw up blue prints | 2 Days |  | CDGA |  |  |
| 3 | Measure site | 1 Day |  | CDGA |  |  |
| 4 | Submit plans city approval | 7 Days |  | CDGA |  |  |
| 4.1 | Survey site | 1 Day |  | CDGA |  |  |
| 4.2 | Stake site | 1 Day |  | CDGA |  |  |
| 5 | Order grader Equip. | Sim |  | CDGA |  |  |
| 6 | Get on Utilities Calander | Sim |  | CDGA |  |  |
|  | Site and architectural plans approval | Sim | X |  |  |  |
| 7 | Grade site-remove debris | 1.5 Days |  | ? |  |  |
| 6.1 | Utilities dig 2 trenches | 2 Days |  | City |  |  |
| 8 | Get on foundation Calander | Sim |  | CDGA |  |  |
| 9 | Get on Carpenters Calendar | Sim |  | CDGA |  |  |
| 10 | Order Windows | Sim |  | CDGA |  |  |
| 8.1 | Order four cement trucks | Sim |  | ? |  |  |
| 6.2 | Utilities connected | 2 Days | X | City |  |  |
| 6.3 | City back fills trenches | .25 days |  | City |  |  |
| 7.1 | Site is final regrade | .25 Days |  | ? |  |  |
| 8.2 | Slab is poured | 1 Day |  | ? |  |  |
|  | Slab foundation finished |  | X | ? |  |  |
| 8.3 | 2-days Dry Time | 2 Days |  | ? |  |  |
| 11 | Order framing Materials | Sim |  | CDGA |  |  |
| 12 | Order Steel Siding | Sim |  | CDGA |  |  |
| 10.1 | Windows Arrive | Sim |  |  |  |  |
| 8.4 | Foundation Inspected | Sim |  | City |  |  |
| 11.1 | Framing Materials Arrive | Sim |  |  |  |  |
| 9.1 | Carpenters arrive | Sim |  |  |  |  |
| 12 | Order Sheet Rock/Insul. | Sim |  | CDGA |  |  |
| 11.2 | Frame base and walls | 1 Day |  | CDGA |  |  |
| 11.3 | Finish Fr. walls/Start Truss | 1 Day |  | CDGA |  |  |
| 11.4 | Finish truss/Start wall boards | 1 Day |  | CDGA |  |  |
| 13 | Plumb/Eletr. rough-in | Sim |  | P&E |  |  |
| 11.5 | Finish walls & windows | 1 Day |  | CDGA |  |  |
| 14 | Start Siding | 4 Days |  | CDGA |  |  |
| 15 | Order Counters/Cab./Floor | Sim |  | CDGA |  |  |
| 16 | Order Appliances | Sim |  | CDGA |  |  |
| 17 | Roof Shingles started | 3 Days |  | CDGA |  |  |
| 13.1 | Plumb/Eletr. Rough Insp. | Sim |  | P&E |  |  |
| 18 | Rock walls/Insul. | 5 Days |  | CDGA |  |  |
| 18.1 | Tape/Mud | 1 Day |  | CDGA |  |  |
| 18.2 | Tape/Mud & Sand | 1 Day |  | CDGA |  |  |
|  | Finish Siding & Shingles | Sim | X | CDGA |  |  |
| 18.3 | Mud & Sand | 1 Day |  | CDGA |  |  |
| 18.4 | Mud & Sand | 1 Day |  | CDGA |  |  |
| 18.5 | Spray ceiling | .5 Days |  | CDGA |  |  |
| 18.6 | Final Mud & Sand | 1 Day |  | CDGA |  |  |
| 15.1 | Install Count/Cab./Floor | 3 Days |  | CDGA |  |  |
| 19 | Paint & Trim | 2 Days |  | Laborer |  |  |
| 5.1 | Order grader Equip. | Sim |  | ? |  |  |
| 16.1 | Install Appliances | Sim |  | CDGA |  |  |
| 19.1 | Finish Paint & Trim | Sim |  | Laborer |  |  |
| 13.2 | Plumb./Eletr. Finish | Sim |  | P&E |  |  |
| 7.2 | Grade Drive/sidewalk | .75 Day |  | ? |  |  |
| 13.3 | Plumb./Eletr. Finish | 2 Days |  | P&E |  |  |
|  | Plumb/Ele. Final Inspect. | Sim | X | City |  |  |
| 8.5 | Order two cement trucks | Sim |  | ? |  |  |
| 8.6 | Pour Drive/Sidewalk | 1 Day |  | ? |  |  |
| 8.7 | 2-days Dry Time | 2 Days |  | ? |  |  |
|  | Driveway & sidewalk finished | Sim | X | ? |  |  |
| 20 | Clean up site | .5 Days |  | Laborer |  |  |
| 21 | Pass final inspection | .25 Days | X | City/CDGA |  |

Task flow network and critical path

Arrange WBS elements in the form of a task-flow network to determine task

dependencies. Determine the critical path, including necessary resource allocation to

achieve project objectives in the appropriate timeframe. Indicate earliest occurrence

times and highlight the critical path. This can be done by flow charting

software.