## RT5
Consider the following CPM project.
Activity | Normal Time | Crash Time | Normal Cost | Crash Cost
A | 9 | 8 | 1970 | 3300
B | 15 | 11 | 9060 | 12650
C | 13 | 9 | 4100 | 5140
D | 11 | 9 | 5170 | 6370
E | 13 | 8 | 3140 | 4400
F | 11 | 7 | 3570 | 4330
G | 10 | 9 | 13830 | 14330
H | 10 | 6 | 1010 | 1260
Calculate the crashing cost per period for each of the activities of the project.
Activity | Crash Cost per period
A
B
C
D
E
F
G
H
Suppose that the critical path of the project is B-D-E-F-G. Which activity would you select to crash and at what cost per period?
Activity to crash =
Crashing cost per priod =