## RT3
Consider the following project.
Activity | Time (days)
A | 11
B | 6
C | 5
D | 11
E | 6
Complete the following table and state the project completion time.
Activity | Time (days) | ES | EF | LS | LF | Slack
A | 11
B | 6
C | 5
D | 11
E | 6
Project completion time =