A contract has been landed to build a custom boat for a lawyer. Relevant data is shown below. The complication is that the lawyer wants delivery in 32 weeks or he will impose a penalty of $375 for each week his boat is late. **NOTE: No activity can be crashed more than two weeks***

DEVELOP A CRASHING SCHEDULE

Crashing Costs

Activity       Immediate predecessor      Normal time      WK1        WK2

K                         -                                           9               $410       $415

L                         K                                          7                125           -

N                        K                                          5                45            45

M                        L                                          4               300           350

J                          N                                         6                50             -

Q                        J,M                                       5               200           225

P                         Q                                          8                 -              -

Y                         Q                                         7               85             90

Z                          P                                          6              90              -

END                   Y,Z