1. Draw the PERT network, identify the earliest and latest start time for each activity and the amount of slack for non-critical activities

**Completion Immediate Earliest Latest Amount**

**Activity Time Predecessor Start Start of Slack**

A 12 ---

B 6 ---

C 4 B

D 5 B

E 4 A

F 2 C,D

G 3 E,F

H 2 E

I 6 D