3. Determine the cost/day for each activity and complete the time-Cost trade-off function for the various possible plans.

**Immediate TIME COST**

**Activity Predecessor Normal Crash Normal Crash Cost/Day**

A --- 7 6 $400 $460

B A 5 3 500 600

C A 4 2 600 780

D B 3 1 200 320

E C 6 3 500 710

F D,E 6 5 500 630

Plan Time Cost

1