A project involving the renovation and modernization of a medical diagnostics.  There are eight major phases to the project:

A. rip out of old wiring and marking of new wireways

B. design, ordering and receipt of equipment

C. rewiring

D. installation of new equipment

E. testing newly installed equipment

F. calibration of equipment

G. retraining and certification of operators (off-site), and

H. operational testing of system with newly certified operators.

Phases A and B may begin simultaneously, if desired.

Phase D cannot commence prior to completion of phases B and C.

Phase G is not to commence prior to completion of phases B and C.

Phases D, E, and F are sequential events.

| Normal times are as given in the table shown below. Activity | normal time | crash time | normal cost | crash cost |
| --- | --- | --- | --- | --- |
| A | 3 | 1 | 9000 | 17000 |
| B | 6 | 3 | 20000 | 40000 |
| C | 2 | 1 | 5000 | 10000 |
| D | 5 | 3 | 18000 | 24000 |
| E | 4 | 3 | 15000 | 18500 |
| F | 3 | 1 | 30000 | 39000 |
| G | 9 | 4 | 80000 | 98000 |
| H | 3 | 2 | 10000 | 20000 |