Please use the following web sites to answer the questions:

Official web site for the Oresund Bridge - http://uk.oresundsbron.com/page/34

An official public information site with up-to-date information on the region, available in English - http://www.tendensoresund.org/en

TCO A:

- 1-What process would you use for identifying project risks for a second Oresund Bridge project? What risks would you raise for each alternative?

- 2-What process would you use for categorizing project risks for a second Oresund Bridge project? How would you actually categorize them?

- 3-What process would you use for ranking project risks for a second Oresund Bridge project? How would you actually rank them?

TCO C:

- 1-How would you identify the key decision paths and options that can be anticipated in the project? What are these key decision paths and options in your opinion?

- 2-How might you use a decision tree analysis to evaluate the alternatives? What numbers would you use in this analysis?

- 3-How might the techniques we have learned so far have helped the first Oresund Bridge project? Why?

TCOs B & D:

- 1-What risks would you add to a risk matrix for this project to build a second Oresund Bridge?

- 2-For the risk you named above, how would you categorize that risk? Please include risk impacts, risk probabilities, risk severity, and risk response categories.

- 3-What types of opportunities might you see for this second Oresund Bridge project?

TCO E

- 1-What information should be contained in your Risk Management Plan for this second Oresund Bridge project?

- 2-What tools and techniques would you use for the second Oresund Bridge to proactively managing risks? Please describe the tool.

- 3-What kinds of outputs would be expected from the Risk Monitoring and Control process?

TCO F

- 1-What factors would need to be considered before developing a risk-based schedule for the new Oresund Bridge Project?

- 2-Given the project description and identified risks, what would be the key factors in your sensitivity analysis? Why?

- 3-Do you think that your analysis would help to determine the effects of the previously identified risks on the project? Why or why not?

TCO G

- 1-As an Oresund Bridge project manager, how would you determine when project work should be contracted out, and how does risk enter into the decision?

- 2-What kinds of contract types might be good to use for the second Oresund Bridge Project?

- 3-Share examples of issues that surfaced in the original Oresund Bridge Project related to contracts. What could have been done to prevent the impact to the contract (if anything)?

TCO H

- 1-What types of items might you include in our new Oresund Bridge project's Risk Management Plan? In what ways would this help mitigate project risk?

- 2-How would you communicate those risks to the appropriate stakeholders so that key decisions regarding risk management can be made?

- 3-What are the key things you have learned this session from our sets of discussions on the second Panama Canal Project that might apply to the second Oresund Bridge Project?

CASE STUDY:

Oresund Bridge Case

Strategic Risk Management in the Oresund Bridge

A project such as the Oresund Bridge, which connects the Danish capital of Copenhagen with Sweden's third-largest city, Malmo, is an engineering marvel. However, project management and a strategic risk analysis were just as important - they allowed the span to be finished an amazing five months ahead of the original target schedule and within budget.

This four-lane motorway and two-lane railway connection consists of a 4-km immersed tunnel, a 4-km reclaimed island and an 8-km bridge containing a cable-stayed main span of 490 meters. With a subsidy from the European Union of DK1 billion, the Oresundsbron Co. financed the DK19 billion (US $2.5 billion) bridge project. Tolls from the traffic using the span over the next 25 to 30 years will be used to repay the loans.

From the beginning, the project management team worked to identify uncertainties and quantify their possible impact on goals, prioritize risks as the basis for action planning, and establish contingency plans in the event of an unfavorable outcome. During the design phase (1993-95), the team focused on technical and cost optimization. For the risk analysis segment, possible impacts were quantified against project cost. The first contract was signed in 1995. Risk management processes then shifted to the opening date, considered the most critical element to total project success

Bridging Uncertainty

During the implementation of risk management processes, the project team discovered some valuable lessons:

- Management commitment to the process and willingness to implement actions are crucial.

- The process must focus on a prioritized set of main objectives— in this case, date of opening.

- Risk management processes must be separated from detailed planning processes—this exercise
tests the strategies within the project.

- The size of a model for a project strategic risk management process is limited to 50 to 100 activities or issues.

- Risk management must start early, when uncertainties are greatest and there is the most to be gained.

- Dedicate time for the action-planning process.

Time and Cost Concerns

Top management initiated and supported all of the risk management processes as they were applied to the entire organization, including the final action-planning process. The project management team carried through. Risk management for the project included:

- Definition

- Identification

- Quantification

- Mitigation action planning

Quantification was based on the Successive Principle, which is used intensively in Scandinavia. Developed by Steen Lichtenberg, a globally recognized project management authority, researcher, consultant
and lecturer based in Denmark, this method enables identifying, modeling and accessing uncertainties in both estimates and schedules.

The technique also includes soft issues in the modeling process, thereby creating a complete overview of all the uncertainties involved in the decision-making process.

The most important aspect for management, however, was the mitigation action planning. These processes, together with the partnership concept that was implemented before signing the contracts, made it possible for the owner to have a very active role. This proactivity throughout the owner's organization and the close cooperation with the contractors led to the timely discovery of potential hazards, anticipating and preventing the need for any expensive last-minute solutions.

Eyeing the Great Divide

The initial risk analysis focused on cost and time schedules and was aimed at supporting the funding and approval process, as well as the bidding process. The project costs were presented through a cumulative
curve and their related uncertainty profile, showing the 10 largest uncertainty factors influencing project cost. The greatest uncertainties were the design process and associated costs, market conditions, and the owner's organization.

In 1995, three major contracts were signed: the tunnel, dredging and reclamation, and the bridge. Implementation of the coast-to-coast installation contracts then began.

Early in 1996, using information available from the civil engineering contractors, individuals directly involved in each major contract performed the analyses. The summary report indicated only a 10 percent chance of opening on target, with the greatest uncertainties being the overall interface management, element fabrication process and owner's organization. To improve the likelihood of project success, an action-planning process was necessary.

Here is the profile of risks they found and the percent probability of the risk occurring (they called this the “Uncertainty Profile” governing meeting the opening date):

- Overall Interface Management, 17%

- Element Fabrication Process, 14%

- Tunnel Owners Org, 12%

- Tunnel joint Venture, 4%

- Bridge Accidents, 3%

- Tunnel Accidents, 3%

- Tunnel Design, 3%

- Tunnel Labor and Material, 3%

- Bridge Climate, Weather, 3%

- R Test Conditions, 2%

Contingency Planning

The action-planning processes helped create a common understanding of the uncertainties pertaining to each contract. It also helped to focus all activities on avoiding and mitigating the effects of the identified risks.

A second summary report included the influences from a set of defined actions. Management requested that the contract directors identify additional actions that could safeguard a realistic opening date in 2000, and this process helped each main contract director focus on the opening date even more rigorously.

In 1997, based upon actual progress in all of the contracts and input from each of the teams, the planning group began developing a new foundation for a third risk management process. Risk analyses
were performed for the tunnel, dredging, bridges and coast-to-coast installation contracts. Participation was more limited than in the initial analyses, and only those who had direct contact with bridge production participated.

Based on the summary report, management still considered the uncertainties too large and the chances for opening in 2000 too slim. As a result, team members for the main contracts were asked to create new action plans to secure the opening in 2000. All departments were asked for actions that could make a 1 October 2000 opening date possible. A second summary report, including these action plans, generated discussion of a "parallel works" idea for the installation and finishing work.

Efficient Scheduling

Working in parallel meant that all slack in the schedule would be put to productive use. Using this strategy, the team felt it was able to guarantee a 1 July 2000 opening. As part of discussions with the contractors concerning the parallel works idea, a fourth risk analysis was performed for the three main contracts, and the results confirmed that it was safe to plan to open the link on 1 July 2000. Change orders to implement new contract milestones were signed with all contractors. Exhibit 2 compares the outcome of the analysis (expected opening date with related uncertainty shown as the standard deviation) and management objectives for the opening date.

No additional risk analyses were performed or required after June 1998—two years before the opening date. The contractors and the owner's organization focused on and worked toward the same goal. From that point, all deviations from the program were handled rapidly and in a cooperative manner, assisted by a subsequent "musketeer" (all for one and one for all) bonus agreement. Queen Margrethe II of Denmark and King Carl XVI Gustaf of Sweden opened the link on 1 July 2000.

Benefits Achieved

To fully implement risk management, the project required both external consultants (1,200 hours) and internal resources (1,500 to 2,500 hours), but the cost of resources was only a fraction of the benefit of opening ahead of schedule for both the contractors (who worked more effectively) and the owner (who derived early income). In addition, because the project was completed within budget and ahead of schedule, management had no difficulty concluding that the risk analysis had been integral to the successful completion of the Oresund link.