Questions:

Assume you have a project with 10 activities labeled A-J (immediately following). Derive the earliest completion time (or early finish—EF), latest completion time (or late finish –LF), and slack for each of the following task (begin at time = 0). Which tasks are on the critical path? Highlight the critical path on your PERT chart.

| Activity | Preceding Event | Expected Duration | EF | LF | Slack | Critical Path |
| --- | --- | --- | --- | --- | --- | --- |
| A | - | 4 |  |  |  |  |
| B | A | 5 |  |  |  |  |
| C | A | 6 |  |  |  |  |
| D | A | 7 |  |  |  |  |
| E | A,D | 6 |  |  |  |  |
| F | C,E | 5 |  |  |  |  |
| G | D,E | 4 |  |  |  |  |
| H | E | 3 |  |  |  |  |
| I | F,G | 4 |  |  |  |  |
| J | H,I | 5 |  |  |  |  |

Draw a Gantt chart for the tasks shown in the problem above.