CPM/PERT

1.						               Immediate	      Duration

Activity				  Predecessors	       (days)

a. organize layout team			-		5

b. organize modification team			-		3

c. design personnel jobs			a		2

d. set machinery in place			b		3

e. connect utilities				c,d		7

f. modify conveyor system			e		4

g. train personnel				e		3

h. finishing touches				f		5

i. run test lot					g		2

- Draw the project management network.

- Determine the project completion time.

- What is the critical path?

  - A manufacturing company is planning to use PERT to setup a project for a new production line. For this project, they have established the following activities, precedence relationships, and time estimates in days:

Most

Immediate	Optimistic	Likely   Pessimistic

Activity	Predecessors	      to		   tm	       tp

a		       --		      8		   10	      12

b		       --		      6		    7	        9

c		       b		      3		    3	        3

d		       a		    10		  15	      20

e		       d		      6		   7	        8

f		       c		      9		  10	      11

g		       d		      5		   7	      10

h		       e,f		    14		  15	      16

- Draw the project management network.

- Determine the project completion time.

- What is the critical path?