Additional Crashing Problem

A different version of the software product (from last week’s problems) is also being considered.  The activities necessary for the completion of this are listed in the table below.

| Activity | Normal Time | Crash Time | Normal Cost | Crash Cost/wk | Immediate Predecessor |
| --- | --- | --- | --- | --- | --- |
| A | 4 | 3 | 2,000 | 400 | - |
| B | 5 | 3 | 2,200 | 300 | A |
| C | 3 | 3 | 500 | ----- | - |
| D | 8 | 4 | 2,400 | 50 | A |
| E | 6 | 3 | 900 | 150 | B |
| F | 3 | 2 | 3,000 | 600 | C |
| G | 4 | 2 | 1,700 | 700 | D,E |

Indirect costs = $450/week

Penalty = $100/week after week 12 (penalty is in effect at week 13)

Bonus (one time) = $2500 at week 8

(a) 	What is the expected completion time for the project?

(b)	What is the critical path?

(c)	What is the critical path after crashing?

(d)	What is the optimal time for the project?

(e)	What is the total cost of the project after crashing?