| Activity | Description | Predecessor | Normal Time (weeks) | Normal Cost | Crash Time (weeks) | Crash Cost |
| --- | --- | --- | --- | --- | --- | --- |
| A | Finalize site and building contracts | --- | 7 | $7,500 | 4 | $11,500 |
| B | Select local printer | A | 3 | $500 | 2 | $800 |
| C | Hire production manager | A | 3 | $1,200 | 2 | $1,700 |
| D | Design promotional Web site | B | 5 | $6,000 | 3 | $9,000 |
| E | Set TV deal | D | 6 | $4,000 | 4 | $6,500 |
| F | Hire director | E | 4 | $1,200 | 3 | $1,700 |
| G | Plan for TV camera placement | F | 2 | $500 | 2 | $500 |
| H | Target headline entertainers | B | 4 | $2,000 | 3 | $3,500 |
| I | Target support entertainers | H | 4 | $2,000 | 3 | $3,500 |
| J | Travel accommodations for talent | I | 10 | $9,000 | 7 | $16,000 |
| K | Set venue capacity | C | 2 | $300 | 1 | $400 |
| L | Ticketmaster contract | D | 3 | $1,400 | 2 | $1,900 |
| M | On-site ticketing | L | 8 | $7,000 | 6 | $11,000 |
| N | Sound and staging | C | 6 | $9,000 | 5 | $12,000 |
| O | Passes and stage credentials | G | 7 | $4,000 | 5 | $5,800 |
| P | Travel accommodations for staff | B | 20 | $15,000 | 15 | $23,000 |
| Q | Hire sponsor coordinator | B | 4 | $600 | 3 | $800 |
| R | Finalize sponsors | Q | 4 | $1,000 | 3 | $1,400 |
| S | Define/place signage for sponsors | R | 3 | $3,000 | 2 | $4,200 |
| T | Hire operations manager | A | 4 | $1,200 | 2 | $1,800 |
| U | Develop site plan | T | 6 | $6,000 | 5 | $8,500 |
| V | Hire security director | T | 7 | $1,500 | 5 | $3,000 |
| W | Set police/fire security plan | V | 4 | $1,000 | 3 | $1,600 |
| X | Power, plumbing, AC, toilet services | U | 8 | $4,000 | 6 | $7,000 |
| Y | Secure merchandise deals | B | 6 | $6,000 | 3 | $7,500 |
| Z | Online merchandise sales | Y | 6 | $5,000 | 4 | $7,500 |