Conveyor Belt Project – Part 1

Project Description

The new computer-controlled conveyor belt is an exciting project that moves and positions items on the conveyor belt within <1 millimeter.  The proposed project will produce a new system for future installations, and for replacement of those in the field, at a low cost.  The computer-controlled conveyor belt has the potential to be a critical unit in 30 percent of the systems installed in factories.  The new system is also easier to update with future technologies.

| Hardware | Hardware specifications Hardware design Hardware documentation Prototypes Order circuit boards Assemble preproduction models |
| --- | --- |
| Operating system | Kernel specifications Drivers Disk drivers Serial I/O drivers Memory management Operating system documentation Network interface |
| Utilities | Utilities specifications Routine utilities Complex utilities Utilities documentation Shell |
| System integration | Architectural decisions Integration first phase System hard/software test Project documentation Integration acceptance testing |

- Each work package will represent an activity.

- A seven-day workweek is used for the whole year; no holidays.

- An 8-hour workday, or 56-hour workweek, is used.  Overtime is not allowed.

- The project should start January 1 of the next year.

| Activity | Description | Duration (days) | Preceding Activity |
| --- | --- | --- | --- |
| 1 | Architectural decisions | 25 | - |
| 2 | Hardware specifications | 50 | 1 |
| 3 | Kernel specifications | 20 | 1 |
| 4 | Utilities specifications | 15 | 1 |
| 5 | Hardware design | 70 | 2 |
| 6 | Disk drivers | 100 | 3 |
| 7 | Memory management | 90 | 3 |
| 8 | Operating system documentation | 25 | 3 |
| 9 | Routine utilities | 60 | 4 |
| 10 | Complex utilities | 80 | 4 |
| 11 | Utilities documentation | 20 | 4 |
| 12 | Hardware documentation | 30 | 5 |
| 13 | Integration first phase | 50 | 6,7,8,9,10,11,12 |
| 14 | Prototypes | 80 | 13 |
| 15 | Serial I/O drivers | 130 | 13 |
| 16 | System hard/software test | 25 | 14,15 |
| 17 | Order circuit boards | 5 | 16 |
| 18 | Network interface | 90 | 16 |
| 19 | Shell | 60 | 16 |
| 20 | Project documentation | 50 | 16 |
| 21 | Assemble preproduction models | 30 | 17F-S,lag 50 days |
| 22 | Integration acceptance testing | 60 | 18,19,20,21 |