## Sheet1
|  |  |  | Timeline | [12 empty] | Responsibility Matrix
S.No | Milestone | Milestone (T) | Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | Responsible ( R) | Accountable (A) | Consulted © | Informed (I)
1 | Training Strategy completion | T0 | Training Strategy Team Identification (T0-A) | [13 empty] | Project Manager | Project Manager | Busines Leadership, HR Leadership, HR Core Team | Busines Leadership, HR Leadership, HR Core Team, IT Team, Finance Team
Training Strategy Formulation and Stakeholder Consensus (T0-B)
Training Project Charter Roll-out (T0-C)
2 | Training Design completion | T1 | Training design compelted as from T0 | [13 empty] | Project Manager | Project Manager | Business, HR Leadership | HR Core Team, IT
3 | Training Deployment | T2 | Training calendar finalized | [13 empty] | HR Core Team | HR Core Team, IT Staff | Project Manager | Business, HR Leadership
Training methods selected
Training administered
4 | Training Evaluation | T3 | Training evaluated on goals of training program | [13 empty] | HR Core Team | HR Core Team, Project Manager | Project Manager | Business, HR Leadership
5 | Post Training Feedback | T4 | Training improvement steps identified | [13 empty] | HR Core Team |  | Project Manager | Business, HR Leadership
6 | Corrective Training | T5 | Feedback is incorporated in the training to create revised plan | [13 empty] | Project Manager | HR Core Team, IT Staff | Business, HR Leadership | Business, HR Leadership, Finance
Project Stakeholders
1 | Project Manager
2 | HR Leadership
3 | Business Leadership
4 | HR Core Team
5 | IT Team
6 | Finance