## answer
Organizers for a political convention have determined ten activities that must be done before the convention begins.
Activity Immediate Predecessors Time (Weeks)
A --- 10
B A 4
C B 2
D B 2
E A 6
F A, C 3
G D 4
H F, G 6
I D 5
J E 4
Please:
a. Draw out the PERT/CPM network for the project.
b. Identify the critical path.
c. Determine how many weeks prior to the convention the work must begin.
| Activity | Immediate Predecessors | Time (Weeks) | Remarks
| A | --- | 10 |  |  |  |  | A --- 10
| B | A | 4 |  |  |  |  | B A 4
| C | B | 2 |  |  |  |  | C B 2
| D | B | 2 |  |  |  |  | D B 2
| E | A | 6 |  |  |  |  | E A 6
| F | A,C | 3 | Since C can come only after B which comes after A it effectively means C is the immediately preceding activity |  |  |  | F A, C 3
| G | D | 4 |  |  |  |  | G D 4
| H | F,G | 6 |  |  |  |  | H F, G 6
| I | D | 5 |  |  |  |  | I D 5
| J | E | 4 |  |  |  |  | J E 4
a. Draw out the PERT/CPM network for the project.
The PERT?CPM network is drawn below
Activity Node
Earliest StartTime
Latest Completion Time
4
16
17
[8 empty] | C | 2 |  | F
3
| 0 | A |  | 1 | B |  | 3 | D |  | 5 | G |  | 6
| 0 | 10 |  | 10 | 4 |  | 14 | 2 |  | 16 | 4 |  | 20
| 0 |  |  | 10 |  |  | 14 |  |  | 16 |  |  | 20 | H
6
E
|  |  | 6 | [10 empty] | I
[14 empty] | 5 | 7
26
26
J
[5 empty] | 2 |  |  |  |  | 4
6
22
b. Identify the critical path.
The critical path is identified using the blue arrow
This is the sequence A-B-D-G-H
The critical path has been identified using the nodes where Earliest start time = Latest completion time
An activity (i,j) lies on the critical path if it satisfies the following three conditions:
(I,j represents the start and completion node) Thus activity A has nodes 0 and 1, C has nodes 3 and 4.
1) | ESi= LCi
2) | ESj= LCj
3) | ESj-ESi= LCj-Lci= Dij
Let us check whether activities A,B,D,G,H have these characteristics
| Activity | Starting node | Ending node | Duration Dij | ESi | ESj | LCi | LCj | ESi= LCi | ESj= LCj | ESj-ESi= LCj-Lci= Dij | Critical Activities
| A | 0 | 1 | 10 | 0 | 10 | 0 | 10 | Yes | Yes | Yes | Critical
| B | 1 | 3 | 4 | 10 | 14 | 10 | 14 | Yes | Yes | Yes | Critical
| C | 3 | 4 | 2 | 14 | 16 | 14 | 17 | Yes | No | No | NC
| D | 3 | 5 | 2 | 14 | 16 | 14 | 16 | Yes | Yes | Yes | Critical
| E | 0 | 2 | 6 | 0 | 6 | 0 | 22 | Yes | No | No | NC
| F | 4 | 6 | 3 | 16 | 20 | 17 | 20 | No | Yes | No | NC
| G | 5 | 6 | 4 | 16 | 20 | 16 | 20 | Yes | Yes | Yes | Critical
| H | 6 | 7 | 6 | 20 | 26 | 20 | 26 | Yes | Yes | Yes | Critical
| I | 5 | 7 | 5 | 16 | 26 | 16 | 26 | Yes | Yes | No | NC
| J | 2 | 7 | 6 | 26 | 22 | 26 |  | Yes | No | No | NC
Indded activities A,B,D,G,H have these characteristics
Thus we have identified the critical path correctly
c. Determine how many weeks prior to the convention the work must begin.
The length of critiacl path =
Duration
| A= | 10
| B= | 4
| D= | 2
| G= | 4
| H= | 6
| Total | 26 | weeks
| Therefore |  | 26 | weeks prior to the convention the work must begin