## Sheet1
1
Construct a network information from the information in the following table and identify all the paths in the network, compute the length of each, and indicate the critical path.
Activity | Activity Predecessor | Time (Weeks)
1 | - | 7
2 | - | 10
3 | 1 | 6
4 | 2 | 5
5 | 2 | 4
6 | 3.4 | 3
7 | 5.6 | 2
2
Determine the earliest start and finish times, latest start times, and slack for each activity. Indicate how the critical path would be determined from this information.