## Sheet1
Construct a Gantt chart for the project described by the following set of activities, and indicates the project completion time and available slack for each activities
Activity | Activity Predecessor | Time (Weeks)
1 | - | 3
2 | - | 7
3 | 1 | 2
4 | 2 | 5
5 | 2 | 6
6 | 4 | 1
7 | 5 | 4