Critical Path

The following table provides the optimistic, most likely and pessimistic times for a project which has five activities. Use this information to solve the followings questions.

Activity	Optimistic	  Most Likely  Pessimistic	Precedent

A		3		4		5		--

B		5		8		12		A

C		8		9		10		A

D		1		2		3		B,C

E		3		4		5		D

- Find the earliest expected completion date of the project

- Find variance for activity C

- Find the variance of critical path

- Find early finish time for activity C