Consider the tasks, durations, and predecessor relationships in the following network.

| Activity Description | Immediate Predecessor(s) | Optimistic (Weeks) | Most Likely (Weeks) | Pessimistic (Weeks) | Te | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| A | --- | 4 | 7 | 10 |  |  |
| B | A | 2 | 8 | 20 |  |  |
| C | A | 8 | 12 | 16 |  |  |
| D | B | 1 | 2 | 3 |  |  |
| E | D, C | 6 | 8 | 22 |  |  |
| F | C | 2 | 3 | 4 |  |  |
| G | F | 2 | 2 | 2 |  |  |
| H | F | 6 | 8 | 10 |  |  |
| I | E, G, H | 4 | 8 | 12 |  |  |
| J | I | 1 | 2 | 3 |  |  |

- Draw the network:

- Calculate Te for all tasks (fill in the table):

- Calculate variance for all tasks (fill in the table):

- Determine all paths, their estimated durations, and their variances:

- Identify the critical path:

- What is the likelihood (probability) of completing the project in 42 weeks?