Problem

| Activity | Mean Duration (Days) | Std. Dev. (Days) |
| --- | --- | --- |
| A | 11 | 0.9 |
| B | 13 | 1.1 |
| C | 7 | 0.2 |
| D | 9 | 0.8 |
| E | 6 | 1 |
| F | 7 | 1.2 |
| G | 10 | 0.7 |
| H | 9 | 0.6 |
| I | 8 | 0.8 |

- Calculate the project completion time.

- Indicate the critical path activities.

- What is the probability of completing this project between 38 and 40 days?

- What are the slack values for activities C and F? Interpret the meaning of their slack values?