3.1) A manufacturer of electricity and steam cogeneration systems produces low-cost and environmentally sound turbine/generator sets for use at locations were steam is to be consumed. The project network for a segment of manufacturing activities is shown below.

| Activity | Mean time (weeks) | Standard Deviation (weeks) | Crash Data |
| --- | --- | --- | --- |
|  |  |  | Time Reduction (weeks) | Cost Slope ($ per week) |
| A | 7 | 2 | 0 | - |
| B | 3 | 0 | 2 | 500 |
| C | 5 | 2 | 2 | 1500 |
| D | 17 | 2 | 2 | 2000 |
| E | 13 | 3 | 2 | 1000 |
| F | 5 | 1 | 0 | - |
| G | 10 | 2 | 1 | 6000 |
| H | 6 | 2 | 3 | 3000 |
| I | 2 | 1 | 1 | 1000 |

- Determine the start and finish times, slack of each activity and the expected project completion time. Identify the critical path.

- What is the probability of completing the project in 35 weeks or less?

- If, simultaneously, activity E is shortened by 2 weeks and activity G is shortened by 1 week, what effect would this have on the completion date?

- (Refer back to the original problem, ignore the modifications made in part (c) ) If the expected project completion time is to be reduced by 3 weeks, what will be the minimum additional cost and what activities will be crashed?

MY WORK:

ES		EF		LF		LS

A		0		7

B		7		10		1O		7

C		7		12		24		19

D		7		24		24		7

E		10		23		29		16

F		24		29		29		24

G		29		39		39		29

H		24		30		39		33

I		39		41		41		39

# Text boxes

A

C

B

H

D

G

E

F

I